# Sprint Progress Report — PG-S2-47

Table of Contents

# Sprint Progress Report

Project: PG-S2-47 — Hydrogen Production Materials Discovery Using Deep Neural Networks Prepared for: Dhika Pratama, Academic Supervisor Prepared by: Alex Tanui, on behalf of the project team Team: Alex Tanui, Fazin Faizal, Ruturaj Yashwant Bhosale, Shijin Mathew, Dongxiao Wu Date: 1 October 2026 Covering: Sprint 0 through Sprint 4

## Introduction

This report summarises the team’s progress across the first five sprints of the project, covering the initial project setup through the Phase 1 atomistic-model baseline bake-off and the start of Phase 2 uncertainty modelling. Each section covers one sprint: its goal, the work completed and by whom, the deliverable produced, and a short retrospective reflecting on what worked well and what the team is carrying forward into the next sprint.

The technical programme follows the three-phase research plan agreed with the project’s academic supervisor: a deterministic baseline model (Phase 1) predicting molecular energy and forces, followed by two approaches to quantifying that model’s uncertainty — reproducing the BLIP method (Phase 2) and the team’s own graph-space contribution (Phase 3). Sprints 0 through 4, covered here, take the project from initial setup through the completion of Phase 1 and the beginning of Phase 2.

## Sprint 0 — Project Setup

Dates: 18–24 August 2026

### Sprint Goal

Establish the team’s working infrastructure — source control, project tracking, and initial data access — so that all subsequent sprints have a stable foundation to build on.

### Summary

This sprint focused on the operational groundwork required before any technical work could begin. Alex Tanui, as Scrum Master and Technical Lead, established the GitHub repository and the Jira project board, and carried out the initial download and staging of the MD17/MD22 molecular dynamics datasets. Alex also authored the project’s foundational documentation — glossary.md and ROADMAP.md — setting out the team structure, folder ownership, and a ten-week execution plan.

Dongxiao Wu began reviewing the unit’s Sprint Review and Backlog requirements, to ensure the team’s working process would meet the assessment criteria from the outset. Ruturaj Yashwant Bhosale, Fazin Faizal, and Shijin Mathew were onboarded to the repository and began familiarising themselves with the project scope in their respective areas: modelling, QA/benchmarking, and data engineering.

### Deliverable

A structured, version-controlled repository; a live Jira project with the team’s epics defined; and full team access to both.

### Retrospective

What went well: Team roles and folder ownership were documented from day one, giving every later sprint a clear reference for who owns what. Source control and project tracking were both operational before any technical work began, rather than introduced partway through.

What could be improved: Hour estimates were not recorded against the setup tasks completed this sprint. This is addressed as an action item below and carried forward until resolved.

Action items for next sprint: Begin recording hour estimates on all Jira issues, retroactively where practical and prospectively from Sprint 1 onward.

## Sprint 1 — System Architecture and Research Grounding

Dates: 25–31 August 2026

### Sprint Goal

Define and freeze the system’s technical architecture and data model, so that all subsequent development — across five team members working in parallel — builds against a single, agreed specification.

### Summary

This sprint produced the architectural foundation the project has built on ever since. Alex Tanui authored the system architecture (summarised below), together with the API contracts and data schema that all later code was written against. Dongxiao Wu began the literature review underpinning the project’s Phase 1 modelling choices, starting with Gilmer et al. (2017) on message-passing neural networks and Schütt et al. (2017) on SchNet. Ruturaj Yashwant Bhosale began early prototyping of a message- passing network against the MD17 dataset, and Shijin Mathew began reviewing the raw data inventory ahead of the cleaning work scheduled for Sprint 2.

### System Architecture

The project is structured as three independently runnable layers, with a dependency that flows in one direction only:

┌─────────────────┐      ┌──────────────────────┐      ┌──────────────────┐
│   ml/            │      │   backend/            │      │   frontend/        │
│   (research core) │─────▶│   (FastAPI service)   │─────▶│   (React dashboard) │
└─────────────────┘      └──────────────────────┘      └──────────────────┘
        │                          │
        ▼                          ▼
  experiments/               backend/app.db
  (configs, checkpoints,     (prediction logs)
   results)

ml/ is the research core and the project’s primary technical deliverable. It contains the data pipeline (ml/data/), the model implementations (ml/models/ — one file per architecture), the training and evaluation code (ml/training/), and shared utilities for metrics and configuration (ml/utils/, ml/config.py). This layer has no dependency on the backend or frontend and can be run and tested entirely on its own.

backend/ is a FastAPI service that loads a trained checkpoint from ml/ and serves predictions over HTTP, exposing endpoints for predictions, model benchmarking, and molecule lookup. It does not duplicate any modelling logic.

frontend/ is a React/Vite dashboard that communicates with the backend exclusively through a single API client module.

The underlying data is staged in three tiers, maintained by Shijin Mathew: bronze (raw, as-downloaded files), silver (deduplicated and format-validated), and gold (production-ready, with the train, validation, and test split applied). Only the gold tier is read during model training, ensuring every experiment runs against identical, validated data.

Each molecular structure is represented as a graph: atoms are nodes (embedded by atomic number), and edges connect atom pairs within a 5 Ångström cutoff radius, with interatomic distance as the edge feature. This representation was selected in preference to string-based encodings such as SMILES, which do not capture the three-dimensional geometry required for energy and force prediction.

### Deliverable

glossary.md and ROADMAP.md — the architectural and scheduling specification against which all subsequent sprints’ work has been reviewed.

### Retrospective

What went well: Freezing the architecture before any model code was written meant that, when five team members later developed five different model architectures in parallel (Sprint 3), none of the work collided on interface design — every model was built against the same specification from this sprint.

What could be improved: The architecture originally specified a single shared model backbone reused across all three research phases. That assumption was revised in Sprint 3, when the team moved to a comparative evaluation of five architectures for Phase 1. This was a reasonable and well-justified adjustment, but it is noted here as a change from the original plan rather than something anticipated at this stage.

Action items for next sprint: Begin the data cleaning and validation pipeline against the frozen data schema; begin defining the Phase 1 evaluation protocol.

## Sprint 2 — Data Pipeline and Platform Scaffolding

Dates: 1–10 September 2026

### Sprint Goal

Deliver a complete, validated MD17 data pipeline — from raw source files through to model-ready data — that all subsequent modelling work can rely on without further changes to the underlying data.

### Summary

Shijin Mathew completed the bronze-to-silver data cleaning stage, resolving format duplication across several molecules in the dataset and unifying every source file under a consistent schema, tagged by molecule and level of quantum-chemical theory. Fazin Faizal defined the Phase 1 evaluation protocol and implemented the first version of the energy and force accuracy metrics used throughout the project. Alex Tanui began scaffolding the backend API and frontend dashboard against the contracts defined in Sprint 1. Dongxiao Wu continued the Phase 1 literature review.

### Deliverable

A fully implemented data pipeline (ml/data/), producing validated gold- stage data for the full MD17/MD22 dataset roster; accompanying documentation in docs/data_dictionary.md; and an exploratory data analysis notebook covering the gold-stage data.

### Retrospective

What went well: The data pipeline delivered this sprint has not required any rework since — every model trained in later sprints reads from the same gold-stage data produced here. Validation (shape, missing- value, and unit checks) was built into the pipeline from the outset.

What could be improved: Platform scaffolding work extended beyond this sprint’s window and remained the project’s slower-moving track into Sprint 3. Hour estimates continue to be absent from Jira issues closed this sprint.

Action items for next sprint: Begin the Phase 1 model implementation and training; continue platform scaffolding to completion; begin recording hour estimates on new and existing issues.

## Sprint 3 — Phase 1 Baseline Bake-off

Dates: 11–21 September 2026

### Sprint Goal

Each team member implements and, where possible, trains one atomistic model architecture against an identical dataset, split, and evaluation protocol, so that the five resulting models can be fairly compared and the strongest candidate selected as the Phase 1 baseline for later uncertainty-modelling work.

### Summary

This was the largest sprint to date, and reflected a deliberate expansion of scope agreed by the team and supervisor: rather than a single shared model, the team undertook a comparative bake-off of five established architectures from the molecular machine-learning literature — MPNN, SchNet, PaiNN, DimeNet++, and PhysNet — one per team member.

Ruturaj Yashwant Bhosale implemented the MPNN baseline and, alongside it, the shared configuration system and training loop that the rest of the team’s models now train through. In the course of this work, Ruturaj identified and corrected a subtle but significant bug in the force calculation: the model was computing forces from pre-stored edge features with no gradient connection back to atomic positions, which would have silently produced zero forces without raising an error.

Alex Tanui implemented the SchNet baseline, using continuous-filter convolutions over the molecular graph, and trained it for the full 200- epoch budget on the complete training dataset. This is currently the only fully trained result in the bake-off evaluated under directly comparable conditions: an energy mean absolute error of 0.0873 kcal/mol and a force mean absolute error of 0.1114 kcal/mol per Ångström, with full training and inference timing recorded. A detailed model card and an interactive results dashboard were produced for this result. The same force- calculation issue Ruturaj identified was independently found and documented here, for the benefit of the remaining entries.

Fazin Faizal implemented the PaiNN baseline — an equivariant architecture that, unlike the other four, represents directional information between atoms rather than distance alone. Beyond the model itself, Fazin built two pieces of shared infrastructure that the whole team now depends on: a model-agnostic evaluation harness, and a model registry standardising how a trained checkpoint records which architecture produced it. Extensive automated tests, including checks of the model’s rotational-equivariance properties, accompany this work. Training was not yet completed at the time of writing, as the shared training loop was not available until later in the sprint.

Dongxiao Wu implemented the DimeNet++ baseline and carried out an in-depth training analysis across multiple epoch budgets, including dedicated investigations into energy prediction bias and calibration. This analysis was conducted on the CCSD(T) level of theory for ethanol, a smaller and higher-accuracy reference dataset than the DFT-level data used for the other four models; results from this entry will need to be re-run on the shared dataset before they are directly comparable to the rest of the bake-off.

Shijin Mathew implemented the PhysNet baseline, including comprehensive unit testing, and trained it on a representative subset of the data due to CPU training-time constraints identified during the sprint (a full run was estimated at several days on the available hardware). Shijin also conducted integration testing across the team’s branches, identifying and documenting an interface inconsistency between two team members’ work before it could affect downstream results.

### Deliverable

Five implemented model architectures, each conforming to a shared interface; a shared training and evaluation harness and model registry, neither of which existed at the start of the sprint; one fully trained and directly comparable result (SchNet); and three further results at varying stages of completion, each documented transparently with respect to its comparability to the others.

### Retrospective

What went well: The architectural discipline established in Sprint 1 allowed five team members to build five different models in parallel with no interface conflicts. The team’s quality-assurance process functioned well in practice: the same critical bug — forces silently computed with no gradient path to atomic positions — was independently identified and documented by three different team members, each flagging it for the benefit of the others rather than treating it as solved once found. Two team members built shared infrastructure beyond their own ticket’s scope because they recognised gaps that would otherwise have affected others’ work.

What could be improved: The bake-off’s comparison is not yet on equal footing across all five entries — only the SchNet result is trained on the full shared dataset for the full training budget. A fair comparison, and the selection of a Phase 1 baseline, depends on bringing the remaining entries onto comparable terms. Available compute capacity (CPU-only training) proved to be a tighter constraint than anticipated and should be factored into planning for Phase 2, where training cost is expected to increase further.

Action items for next sprint: Complete training for PaiNN and MPNN through the now-available shared training loop; re-run the DimeNet++ baseline on the shared dataset; agree a consistent, realistic training budget for PhysNet; and consolidate the team’s work, currently spread across five separate branches, into the main branch.

## Sprint 4 — Phase 2 Initiation (In Progress)

Dates: 22 September – 3 October 2026. This sprint is in progress at the time of writing; the summary below reflects the project’s status as of 1 October 2026 and will be updated at the sprint’s close.

### Sprint Goal

Bring the Phase 1 bake-off to a fully comparable conclusion, and begin Phase 2 by implementing BLIP-style weight-space uncertainty on top of the selected Phase 1 baseline.

### Summary

Work this sprint is proceeding on two fronts. First, completing the Phase 1 convergence work carried over from Sprint 3 — bringing the remaining model entries onto comparable footing. Second, beginning Phase 2: Ruturaj Yashwant Bhosale has begun implementing the BLIP mechanism, which introduces input-dependent stochasticity into the model’s weights to produce calibratable uncertainty estimates. Fazin Faizal is profiling compute requirements ahead of the heavier Monte Carlo sampling that Phase 2 evaluation requires, directly applying the compute-planning lesson identified in the Sprint 3 retrospective. The remaining Phase 2 tasks — implementing uncertainty-quality metrics and wiring uncertainty estimates into the platform — are correctly sequenced behind this foundational work and have not yet started.

### Deliverable (in progress)

No Phase 2 implementation has yet landed in the shared codebase as of this report. The team’s near-term deliverable is a finalised, directly comparable Phase 1 result set, which the Phase 2 work depends on.

### Retrospective (interim)

What went well: Dependencies between Phase 2 tasks have been correctly sequenced, so no team member has begun work that depends on an unfinished prerequisite. The compute-planning concern raised in Sprint 3 is being acted on proactively this sprint rather than being rediscovered under time pressure.

What could be improved: Carrying Sprint 3’s unfinished convergence work into Sprint 4 without re-scoping it explicitly has made it harder to track in the project backlog. This is being corrected going forward.

Action items for next sprint: Finalise the Phase 1 comparison and formally select the baseline architecture; land the BLIP implementation against the shared model interface; and continue closing the outstanding hour-estimate gap in the project’s Jira tracking, which remains the team’s most consistent process improvement item across every sprint to date.

## Summary and Outlook

Across Sprints 0 through 4, the team has established a working architecture, built and validated a complete data pipeline, and delivered a comparative evaluation of five candidate model architectures for Phase 1, with one — SchNet — fully trained and evaluated under controlled conditions. Phase 2 work has begun, building directly on the Phase 1 infrastructure.

The team’s main priorities heading into the next sprint are: completing a fully comparable Phase 1 result set across all five architectures, formally selecting the Phase 1 baseline, and progressing the Phase 2 implementation. Process improvements identified across these five sprints — principally, consistent hour estimation in Jira to support accurate burn-up reporting, and more frequent consolidation of team members’ branches into the main codebase — are being carried forward as standing action items.